## Cover Page
Patient Tracker
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Academy - Project Solutions
Role
Signature
| Date | 2019-11-08
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Patient Tracker Project ID: A006 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priority | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Role Selection | Patient, Doctor, Admin, Clerk | Ability of the system to allow a user to choose the required User role for registration | 1. When a visitor opens the web page, the initial screen should display the options to select from the different roles to which a user would like to register. 2. The roles to be displayed as "Patient", "Doctor" "Admin" or "Clerk" | Critical
US_2 | User Registration and Login | User -Patient, Doctor, Clerk | Ability of the system to procure the fundamental details of the Patient, save the user details in the Database and allow user login | 1. When the Users clicks on the registration link, it should re-direct to registration form. 2 User needs to fill some of the basic attributes/fields as mentioned below - User should select their roles. Below fields should be displayed as per the selected role. First Name, Last Name, DOB, Gender, Contact Number, Patient id/Doctor Id/Clerk Id, Password, Doctor's qualification, address, speciality etc. Patient id/Doctor id/ Clerk id - should be autogenerated. Gender - should be selected from the dropdown Contact number - 10 digits password- min length of 6 with special characters should be incorporated. Note - Trainees can add/neglect fields that will be appropriate and validations should be handled for all fields 3. Clicking ‘Submit’ should validate the datatype constraints for each field 4. User failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5. Post-successful field level validation, save the information in the database 6. Upon saving the information in the database, display the message, ‘Your details are submitted succesfully | Critical
US_3 | User Authentication | Patient | Ability of the system to authenticate the credentials of the registered Patient | 1. A registered user – is able to click ‘Login’ link, after keying in ‘User ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. 2. A user whose registration is rejected – is unable to login and get the credentials authenticated, the user is presented with relevant error messages: Invalid User ID (or) Incorrect Password | Critical
US_4 | Admin Registration and Login | Admin | Ability of the system to procure the fundamental details of the Admin, save the user details in the Database and allow user login | 1-Users should have option to select their role option - user/Admin 2-Admin should select the Admin option. 2-Admin's User id and password should be pre-loaded in the database, which can be used to log in. | Critical
US_5 | Admin Authentication | Admin | Ability of the system to authenticate the credentials of the registered Admin | A registered Admin– is able click ‘Login’ link, after keying in 'Admin ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. | Critical
US_6 | User Registration and Login | Clerk | Ability of the system to procure the fundamental details of the Clerk, save the user details in the Database and allow user login | 1. When the user clicks on the "Clerk" role, it should re-direct to registration form 2. Clerk needs to fill some of the basic attributes/fields as mentioned below in requirement: First Name, Last Name, Age, Gender, Contact Number, Clerk Id, Password 3. Clicking ‘Submit’ should validate the datatype constraints for each field 4. User failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5. Post-successful field level validation, save the information in the database 6. Upon saving the information in the database, display the message, ‘Your details are submitted successfully’. | Critical
US_7 | User Authentication | Clerk | Ability of the system to authenticate the credentials of the registered Clerk | 1. A registered user – is able to click ‘Login’ link, after keying in ‘User ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. 2. A user whose registration is rejected – is unable to login and get the credentials authenticated, the user is presented with relevant error messages: Invalid User ID (or) Incorrect Password | Critical
US_8 | Approve / Deny Doctor / Clerk / Patient registration | Admin | Ability of the system to allow admin to approve or deny the registration request. | 1. Admin should be able to approve or deny the registration request. 2. Upon approval, Doctor / Clerk should be able to log in successfully. 3. Upon denial, message should be displayed when they try to log in. | Medium
US_9 | Add / Maintain Patient info | Admin/Clerk | Ability of the system to allow Admin/Clerk to update and maintain Patient Information. | 1. On clicking “Patient Details”, it should redirect to the Page listing Available Patients 2. On clicking Add Patient it should redirect to Patient record creation page 3. Admin / Clerk should be able to update the mandatory fields of the Patient 4. Clicking ‘Submit’ should validate the datatype constraints for each field 5. Admin / Clerk failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 6. Post-successful field level validation, save the information in the database 7. Upon saving the information in the database, display the message ‘Your details are submitted successfully’. 8. From Patient Information page, on clicking the Patient ID, the details of the Patient should be displayed 9. Admin / Clerk on clicking Edit option should be able to edit the Patient Record and save it | Critical
US_10 | Update Test results | Admin | Ability of the system to allow Admin to update the Test result. | 1. Admin on Clicking the Update test result, it should display the entire patient Ids who have raised the Test Request. 2. On clicking the Patient Id, it should populate all the details of the Test Request and Admin should be able to update the Results 3. Admin should maintain the Basic information on each test and the required values for each test. It should also maintain the Baseline values for each test. | Critical
US_11 | View Test Result | Patient/Doctor | Ability of the system to allow Patient / doctor to view the updated test result. | 1. Doctor on clicking View Test result should list all the patient IDs linked to the doctor 2. On clicking the Patient Id, it should list all the Test result Ids and Description of that patient. 3. On clicking the Test Id, it should display all the details 4. Patient on clicking view test results, it should list all the Test result Ids and Description of that patient. 5. On clicking the Test Id, it should display all the details | Critical
US_12 | Update Treatment / prescription details | Doctor | Ability of the system to allow Doctor to update Treatment / prescription details | 1. Doctor on clicking Patient Record link should redirect to the Medical record page 2. Doctor should fill in the necessary details and submit 3. After successful validation the details should be stored to the DB 4. In case any field value is missing, error message should pop up 5. On saving the data, Data saved successfully message should be displayed 6. Doctor on clicking the Update Records, should list all the patient records created by him | Medium
US_13 | Maintain treatment history | Doctor | Ability of the system to allow doctor to maintain the treatment history of the patient | 1. Doctor should be able to update the existing Patient record by clicking the patient ID 2. Data validation to be done as in Req_19 | Medium
US_14 | Update Diet / exercise Recommendations | Doctor | Ability of the system to allow doctor provide Diet / exercise recommendations based on the test results. | 1. Doctor on clicking Update Diet / exercise link should redirect to the Diet recommendation page 2. Doctor should fill in the necessary details and submit. Diet, exercise 3. On saving the data, Data saved successfully message should be displayed 4. Doctor on clicking the Update Records, should list all the patient records created by him 5. Doctor should be able to update the data available in the system | Medium
US_15 | View Diet / exercise Recommendations | Patient | Ability of the system to allow Patient to view Diet / exercise recommendations based on the readings tracked | 1. Patient on clicking View Doctor recommendations link, should redirect to the Diet / Exercise page 2. This page should display the recommendations as suggested by the doctor | Medium
US_16 | In Patient Details | Admin | Ability of the system to allow Admin to maintain inpatient details, Room charges, Admission and discharge details. | 1. On clicking “Create In Patient records”, it should redirect to the In Patient records Details Update Page 2. Admin should be able to update the mandatory fields of the In Patient records. Admin to maintain inpatient details, Room charges, Admission and discharge details. 3. Clicking ‘Submit’ should validate the datatype constraints for each field 4. Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5. Post-successful field level validation, save the information in the database 6. Upon saving the information in the database, display the message, ‘Your details are submitted successfully’. | Medium
US_17 | Billing | Admin/Clerk | Ability of the system to allow the Admin/Clerk to generate bill for patient for the service / consultation / in stay. | 1. Admin / Clerk should be redirected to Bill creation page on clicking “Create Bill” 2. In create Bill Page, it should display the below options. Consultation Stay Prescription Lab Charges Prescriptions Nursing Charges Note: From the options user should be able to select one or more and the based on the selections, the details should be appended to the bill generated. 3. The user should be able to select the applicable option. 4 On clicking Consultation should get the details - Doctor Name, Date, Specilization, Fees 5 On clicking Stay should get the details - Room Type, Tariff, No of days, Total amount (Total amount field should be auto populated from Tariff and No of days. 5. On clicking the Prescription, Prescription IDs awaiting billing should be displayed. On clicking the Prescription ID, the medicine details, Quantity and Amount should be populated from the DB. Total amount should be auto calculated based on the details. 6. Nursing Charges - should be calculated based on the Room type and no of days of stay. Note: For Room Type, Traiff, Nursing charges Trainees can do a data mock up. 7. The Patient details also should be populated 8. Amounts should be summed up and total amount should be displayed 9. Admin / Clerk should have the option to edit the details 10. When Admin / Clerk clicks Generate Bill, the Bill details should be updated 11. Status of the Prescription should be updated as Billed | Critical
US_18 | Help | Patient/Doctor/Clerk | Page to assist the Customers to report technical issues | 1. Portal to display a form that allows user to report the technical issues through Email: Issue Description Send Button 2. Portal to display the Contact number to report issues | Low
US_19 | Other validations | Admin//Patient/Doctor/Clerk | Ability of the system to allow add on validations like Forgot Customer ID, Forgot Password | 1. During registration, System should pop up three secret questions for Password recovery. 2. When the user clicks Forgot User ID, system should ask for the secret questions. On answering the questions correctly, the User ID should be displayed. 3. When the user clicks Forgot Password, system should ask for the User ID and secret questions. On answering the questions correctly, the password reset page should be displayed. 4. On entering the details in the password reset page, password should be validated 5. On clicking Submit, the details should be saved to the Database | Low
US_20 | User logoff | Admin/Patient/Doctor/Clerk | Ability of the system to allow the user to logoff | 1. Option to log off from the system. | Critical

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000